## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2215-swen-261-02-c-straightflush
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | NA; 3/14/22
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | CR; 3/14/22
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Pass | RT; 3/14/22
| Given that I am on the products page, when I enter a search parameter and click Go, it returns the search results | Pass | RT; 3/14/22
| Given that I am on the products page when there are products in the inventory then I see each product and the price | Pass | CR; 3/14/22
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | NA; 3/14/22
As a buyer I want to see a single product so that I can see a product's details. | Given that I am on the e-store site when I am on the Products page I can navigate to an individual product page | Pass | CR; 3/14/22
| Given that I am not on the Products page when I choose the Product I go to the single product page | Pass | RY; 3/14/22
| Given that I go to a products page of a product that does not exist, I am shown a 404 to show that the product does not exist | Pass | RY; 3/14/22
| Given that I am on the product page when the product is in the inventory then I see each product and short description. | Pass | NA; 3/14/22
| Given that I am on the product page when the are product is in the inventory then I see a means to add the product to my shopping cart. | Pass | CR; 3/14/22
As a buyer I want to log in to save my cart | Given that I am on the e-store site when I am not on the Login page them I must see a means to navigate to the Login page | Pass | RT; 3/14/22
| Given that I am not on the Login page when I choose the Login button I go to the login page | Pass | NA; 3/14/22
| Given that I refresh the page I am still logged in | Pass | RY; 3/14/22
As an owner I want to log in | Given that I am on the e-store site when I am not on the Login page them I must see a means to navigate to the Login page | Pass | RT; 3/14/22
| Given that I am not on the Products page when I choose the Login button I go to the login page | Pass | NA; 3/14/22
| Given that I refresh the page I am still logged in | Pass | RY; 3/14/22
As an owner I want to see a single product so that I can see a product's details. | Given that I am on the e-store site when I am on the Products page I can navigate to an individual product page | Pass | RY; 3/14/22
| Given that I am not on the Products page when I choose the Product I go to the single product page | Pass | CR; 3/14/22
| Given that I go to a products page of a product that does not exist, I am shown a 404 to show that the product does not exist | Pass | RY; 3/14/22
| Given that I am on the product page when the product is in the inventory then I see each product and short description. | Pass | NA; 3/14/22
| Given that I am on the product page when the are product is in the inventory then I see a means to add the product to my shopping cart. | Pass | NA; 3/14/22
As an owner I want to edit a single product so that I can change a product's details. | Given that I am on the e-store site when I am on the Products page I can navigate to an individual product page | Pass | NA; 3/14/22
| Given that I am not on the Products page when I choose the Product I go to the single product page | Pass | CR; 3/14/22
| Given that I go to a products page of a product that does not exist, I am shown a 404 to show that the product does not exist | Pass | RY; 3/14/22
| Given that I am on the product page when the product is in the inventory then I see each product and short description. | Pass | NA; 3/14/22
| Given that I am on the product page when the are product is in the inventory then I see a means to delete a product | Pass | RY; 3/14/22
| Given that I am on the product page when the are product is in the inventory then I see a means edit a products name, description, price, and quantity | Pass | NA; 3/14/22
As an buyer I want to add and delete items from my cart so that I can checkout with those items | Given that I am on the e-store site when I am not on the Cart page them I must see a means to navigate to the Cart page
Given that I am not on the Cart page when I choose the Cart button I go to the Cart page
Given that I am on the cart page I can see the items in my cart
Given that I am on the cart page I can delete items from my cart
Given that I am on the cart page I can update the quantity of items in my cart